## screener_checks
message_example | stage | test | migration_notes | new_group | completed | where is currently
All variable names are 50 characters or fewer. | mainTests | variable_name_length | Combine into one 'length' helper | api | No | Screener
All variable labels are 80 characters or fewer. | mainTests | variable_label_length | Combine into one 'length' helper | api | No | Screener
All filter items are 120 characters or fewer. | mainTests | filter_item_length | Combine into one 'length' helper | api | No | Screener
All location names are 120 characters or fewer. | mainTests | location_name_length | Combine into one 'length' helper | api | No | Screener
All location codes are 30 characters or fewer. | mainTests | location_code_length | Combine into one 'length' helper | api | No | Screener
There are no spaces in the variable names in the datafile. | preCheck2 | data_variable_spaces |  | column_names | No | Screener
All variable names are unique in the datafile. | preCheck1 | duplicate_variable_names |  | column_names | No | Screener
The variable names in the data file follow the snake_case convention. | mainTests | variable_snake_case |  | column_names | No | Screener
All variables in the data file start with a lowercase letter. | mainTests | variable_start_letter |  | column_names | No | Screener
Neither characteristic nor characteristic_group were found as listed filters in the meta data file. | mainTests | variable_characteristic |  | column_names | No | Screener
No indicators found containing typical filter entries. | mainTests | indicators_smushed |  | column_names | No | Screener
All variables from the metadata were found in the data file. | preCheck1 | meta_to_data_crosscheck |  | core_structure | No | Screener
There are fewer rows in the metadata file (8) than non-mandatory columns in the data file (31). | fileValidation | rows_to_cols |  | core_structure | No | Screener
The data file does not have any blank columns | fileValidation | data_empty_cols | Can check NA, how about unique() and then compare to ""? | core_structure | In progress | Screener
All of the mandatory columns are present in the data file. | fileValidation | data_mandatory_cols |  | core_structure | No | Screener
All of the mandatory columns are present in the metadata file. | fileValidation | meta_mandatory_cols |  | core_structure | No | Screener
All variables in the data file are observational units or are represented in the metadata file. | mainTests | data_to_meta_crosscheck |  | core_structure | No | Screener
The data file does not have any blank rows. | fileValidation | data_empty_rows | Covered by time_period / identifier / geog_level checks | drop | Yes | Screener
The metadata file does not have any blank rows. | fileValidation | meta_empty_rows | Covered by col_type check | drop | Yes | Screener
The data filename does not have spaces. | fileValidation | data_filename_spaces | Combined into single filename_spaces | filename | In progress | Screener
The metadata filename does not have spaces. | fileValidation | meta_filename_spaces | Combined into single filename_spaces | filename | In progress | Screener
The data filename does not have any special characters. | fileValidation | data_filename_special_characters | Combine into single special_characters | filename | No | Screener
The metadata filename does not have any special characters. | fileValidation | meta_filename_special_characters | Combine into single special_characters | filename | No | Screener
The names of the files follow the recommended naming convention. | fileValidation | naming_convention |  | filename | No | Screener
All filters and groups have a 'Total' aggregation. | mainTests | total |  | filter | No | Screener
There are no Total or All values in the observational unit columns. | mainTests | observational_total |  | filter | No | Screener
There are no blank values in any filters or filter groups. | mainTests | blanks_filters |  | filter | No | Screener
No filters appear to be mislabelled geography columns. | mainTests | geographic_catch |  | filter | No | Screener
No standardised col_name issues found. | mainTests | standard_filter_headers |  | filter | No | Screener
No ethnicity entry issues found. | mainTests | ethnicity_values |  | filter | No | Screener
No ethnicity data found. | mainTests | ethnicity_characteristic_group |  | filter | No | Screener
No ethnicity data found. | mainTests | ethnicity_characteristic_values |  | filter | No | Screener
There are no duplicate rows in the data file. <br> - Note that School, Provider, Institution and Planning area level rows were not included in this test. | mainTests | duplicate_rows |  | general | No | Screener
No problematic NULL or NA values were found in the data or metadata files. | mainTests | null |  | general | No | Screener
No legacy symbols for no data were found in the data file. | mainTests | no_data_symbols |  | general | No | Screener
9 rows of data will be ignored by the table tool. <br> - These will be at School, Provider, Institution and Planning area level. <br> - Please <a href='mailto: explore.statistics@education.gov.uk'>contact us</a> or see our <a href='https://dfe-analytical-services.github.io/stats-production-guidance-copy/ud.html#Allowable_geographic_levels' target='_blank'>guidance website</a> for more information. | mainTests | ignored_rows |  | general | No | Screener
Both region_code and region_name are completed for all Local authority rows in the data file. | mainTests | region_for_la |  | geog | No | Screener
Both region_code and region_name are completed for all Local authority district rows in the data file. | mainTests | region_for_lad |  | geog | No | Screener
All geographic columns are completed as expected. | mainTests | geography_level_completed |  | geog | No | Screener
Where one of region_code or region_name is present, the other column is also present. | mainTests | region_col_present |  | geog | No | Screener
Where one of the local authority columns is present, the other two columns are also present. | mainTests | la_col_present |  | geog | No | Screener
All geographic columns are empty where expected. | mainTests | overcompleted_cols |  | geog | No | Screener
All english_devolved_area_code and english_devolved_area_name combinations are valid. | mainTests | eda_combinations |  | geog | No | Screener
All lsip_code and lsip_name combinations are valid. | mainTests | lsip_combinations |  | geog | No | Screener
All ward_code and ward_name combinations are valid. | mainTests | ward_combinations |  | geog | No | Screener
All local_enterprise_partnership_code and local_enterprise_partnership_name combinations are valid. | mainTests | lep_combinations |  | geog | No | Screener
All pcon_code and pcon_name combinations are valid. | mainTests | pcon_combinations |  | geog | No | Screener
All lad_code and lad_name combinations are valid. | mainTests | lad_combinations |  | geog | No | Screener
All old_la_code, new_la_code and la_name combinations are valid. | mainTests | la_combinations |  | geog | No | Screener
All region_code and region_name combinations are valid. | mainTests | region_combinations |  | geog | No | Screener
All country_code and country_name combinations are valid. | mainTests | country_combinations |  | geog | No | Screener
Every geography has one code. | mainTests | other_geography_duplicates |  | geog | No | Screener
Every geography code has one assigned geography. | mainTests | other_geography_code_duplicates |  | geog | No | Screener
No tested locations have a code of 'x' without the corresponding name 'Not available'. | mainTests | na_geography |  | geog | No | Screener
No tested locations have a name of 'Not available' without the corresponding code 'x'. | mainTests | na_geography_code |  | geog | No | Screener
Obsolete symbols (i.e. ~, : ), are not present in the indicator values. | mainTests | obsolete_symbols |  | indicator | No | Screener
There are no blank values in any indicators. | mainTests | blanks_indicators |  | indicator | No | Screener
All col_name values are unique. | mainTests | col_name_duplicate |  | meta | No | Screener
There are no spaces in the col_name values. | mainTests | col_name_spaces |  | meta | No | Screener
The label column is completed for every row in the metadata. | mainTests | label |  | meta | No | Screener
All labels are unique. | mainTests | duplicate_label |  | meta | No | Screener
No indicators have a filter_hint value. | mainTests | filter_hint |  | meta | No | Screener
No indicators have an filter_grouping_column value. | mainTests | filter_group |  | meta | No | Screener
All filter groups from the metadata were found in the data file. | mainTests | filter_group_match |  | meta | No | Screener
All filter groups have an equal or lower number of levels than their corresponding filter. | mainTests | filter_group_level |  | meta | No | Screener
No filter groups are included in the col_name column. | mainTests | filter_group_not_filter |  | meta | No | Screener
All of the filter_group values are unique. | mainTests | filter_group_duplicate |  | meta | No | Screener
No filter labels contain leading or trailing whitespace. | mainTests | whitespace_filters |  | meta | No | Screener
No filters have an indicator_grouping value. | mainTests | indicator_grouping |  | meta | No | Screener
There are no issues when stripping alpha-numeric characters from filter groups. | mainTests | filter_group_stripped |  | meta | No | Screener
There are no issues when stripping alpha-numeric characters and spaces from indicator groups. | mainTests | indicator_group_stripped |  | meta | No | Screener
No filters have an indicator_unit value. | mainTests | indicator_unit |  | meta | No | Screener
The indicator_unit values are valid. | mainTests | indicator_unit_validation |  | meta | No | Screener
No filters have an indicator_dp value. | mainTests | indicator_dp |  | meta | No | Screener
The indicator_dp column only contains blanks or positive integer values. | mainTests | indicator_dp_validation |  | meta | No | Screener
The indicator_dp column is completed for all indicators. | mainTests | indicator_dp_completed |  | meta | No | Screener
The data and metadata files both appear to use a comma delimited structure. | fileValidation | file_separator | Needs to be on reading of file | pre-file | No | Screener
The data and metadata files are both recognised as using UTF-8 encoding. | preCheck2 | utf8 | Need to think about? Might not be able to do? | pre-file | No | Screener
All filters have two or more levels. | preCheck2 | filter_level | Not sure why this is a pre-check? | pre-filter | No | Screener
The geography columns are present as expected for the geographic_level values in the file. | preCheck2 | geography_level_present |  | pre-geog | No | Screener
The geographic_level values are all valid. | preCheck1 | geographic_level |  | pre-geog | No | Screener
col_type is always 'Filter' or 'Indicator'. | preCheck2 | col_type |  | pre-meta | No | Screener
No observational units have been included in the metadata file. | preCheck2 | ob_unit_meta |  | pre-meta | No | Screener
There are no invalid columns in the metadata file. | preCheck1 | invalid_meta_cols |  | pre-meta | No | Screener
The col_name column is completed for every row in the metadata. | preCheck1 | col_name_completed |  | pre-meta | No | Screener
There is a single, valid time_identifer. | preCheck2 | time_identifier_mix |  | pre-time | No | Screener
The time_identifier values are all valid. | preCheck1 | time_identifier |  | pre-time | No | Screener
The time_period column only contains numeric digits. | preCheck2 | time_validation |  | pre-time | No | Screener
The time_period length matches the time_identifier values in the data file. | mainTests | time_period |  | time | No | Screener
The six digit time_period values refer to consecutive years. | mainTests | time_period_six |  | time | No | Screener

## ees_checks
what | stage | checks | keep
Data/meta file pair upload | general checks | title length should not exceed 120 characters | Yes
Data/meta file pair upload | general checks | ensure associated release version exists | Yes
Data/meta file pair upload | general checks | ensure user has permission for release version | Yes
Data/meta file pair upload | general checks | check for existence of replacing file | Yes
Data/meta file pair upload | general checks | title should not be empty or contain special characters | Yes
Data/meta file pair upload | general checks | title should be unique (unless it’s a replacement) | Yes
Data/meta file pair upload | file validation | data/meta files can’t have the same name | Yes
Data/meta file pair upload | file validation | data/meta file names can’t have spaces or invalid characters | Yes
Data/meta file pair upload | file validation | data file should end “.csv” | Yes
Data/meta file pair upload | file validation | meta file should end “.meta.csv” | Yes
Data/meta file pair upload | file validation | data/meta filenames should not exceed 150 characters | Yes
Data/meta file pair upload | file validation | data/meta file sizes must not be zero | Yes
Data/meta file pair upload | file validation | data/meta files must be valid CSVs - valid MIME types (application/csv, text/csv, text/plain) | Yes
Data/meta file pair upload | file validation | data/meta files must be valid CSVs - valid encoding types (us-acsii, utf-8) | Yes
Data/meta file pair (archived) upload | Valid ZIP file | file name should not exceed 150 characters | Yes
Data/meta file pair (archived) upload | Valid ZIP file | file name ends with “.zip” | Yes
Data/meta file pair (archived) upload | Valid ZIP file | valid MIME types (application/zip, application/x-compressed) | Yes
Data/meta file pair (archived) upload | Valid ZIP file | valid encoding types (binary) | Yes
Data/meta file pair (archived) upload | Valid ZIP file | Archive contains two files | Yes
Data/meta file pair (archived) upload | Valid ZIP file | Data/meta files meet “Data/meta file pair upload” checks | Yes
Bulk ZIP | upload | Archive contains an index file called “dataset_names.csv” | Yes
Bulk ZIP | upload | Index file contains exactly two headers (file_name and dataset_name) | Yes
Bulk ZIP | upload | Index file file_name entries should not end “.csv” | Yes
Bulk ZIP | upload | Index file should not contain duplicate file names or data set names | Yes
Bulk ZIP | upload | Index file should not reference file names which are not present in the archive | Yes
Bulk ZIP | upload | A data set cannot be replaced when a replacement is already in progress | Yes
Bulk ZIP | upload | An archive should not contain files which are not referenced in the index file | Yes
Bulk ZIP | upload | Data/meta files meet “Data/meta file pair upload” checks | Yes
Bulk ZIP | import | The referenced file path exists in temporary blob storage | Yes
processor | import | If it’s an archive, the data/meta files exist in archive | Not needed as will check earlier
processor | import | data/meta files must be valid CSVs - valid MIME types (application/csv, text/csv, text/plain) | Not needed as will check earlier
processor | import | data/meta files must be valid CSVs - valid encoding types (us-acsii, utf-8) | Not needed as will check earlier
processor | meta | contains correct columns (col_name, col_type, label, filter_grouping_column, filter_hint, indicator_grouping, indicator_unit, indicator_dp), filter_default is optional | Replace with screener
processor | meta | rows contain the correct number of columns based on number of headers | Yes
processor | meta | entries column_type is one of “Filter” or “Indicator” | Replace with screener
processor | meta | entries indicator_unit is one of “”, “%”, “£”, “£m”, “pp”, “string” | Replace with screener
processor | data | contains mandatory observation columns (time_identifier, time_period, geographic_level) | Replace with screener
processor | data | rows contain the correct number of columns based on number of headers | Yes

## ees_qa
Note:
- some cases in the BE aren’t entirely relevant for potential screener tests, but behaviours are quite intertwined
- investigation dwindled in depth for UI/FE portion due to reducing relevance, and mostly already covered by BE equivalents
Data/meta file pair upload
Ensure successful execution, and returned value matches request object (unit test - controller)
Ensure validation problem raised in the service layer is returned (unit test - controller)
Ensure successful execution (integration test - multiple)
service returns expected data file details based on request object
content database contains expected file records based on request object
Ensure successful execution with correct release file ordering (integration test - multiple)
service returns expected data file details based on request object
content database contains expected number of file records based on request object, and they are in the correct order
Ensure successful execution with correct replacement behaviour (integration test - multiple)
service returns expected data file details based on request object
stats database contains records for the replacement data as well as the original
content database record has been updated with replacement-specific data (i.e. version number and reference)
Ensure unauthorised user cannot perform uploads (unit test - service)
Data/meta file pair (archived) upload
Ensure unauthorised user cannot perform uploads (unit test - service)
Archive is valid: (unit test - service)
has been provided
is a valid ZIP file
Ensure successful execution (integration test - multiple)
coverage as previous, with additional check for presence of zip file record
Ensure successful execution with correct release file ordering (integration test - multiple)
coverage as previous, with additional check for presence of zip file record
Ensure successful execution with correct replacement behaviour (integration test - multiple)
coverage as previous, with additional check for presence of zip file record
Ensure successful archive validation returns a file summary (integration test - multiple)
Ensure unsuccessful archive validation returns error when only 1 file is present (integration test - multiple)
Bulk ZIP upload
Ensure successful execution returns the appropriate summary view model (unit test - controller)
Ensure unauthorised user cannot perform upload (unit test - service)
Archive is valid (unit test - service) - as above
Ensure successful archive validation returns a file summary (integration test - multiple)
Ensure successful archive validation returns a file summary indicating a file replacement (integration test - multiple)
Ensure unsuccessful archive validation returns error when: (integration test - multiple)
index file is missing
index file has incorrect headers
files referenced in index file aren’t present in archive
index file contains duplicate titles and file names
file names listed in index file are suffixed with “.csv”
archive contains files which haven’t been referenced in index file
Processor import
Ensure import processes expected number of rows (integration test - multiple)
Ensure import processes expected items correctly, and database objects match expected values (integration test - multiple)
filter labels/names/groups/auto-selection
indicator group labels
locations
observations
Ensure content database file object matches expected values (integration test - multiple)
Ensure import failure on observation row count mismatch (integration test - multiple)
Ensure import can successfully resume a partially-completed import process (integration test - multiple)
with expected final row count
when batch size has changed
when some rows should be ignored
Ensure ignored rows are not processed by the importer (integration test - multiple)
Ensure expected number of rows imported when process is cancelled during execution (integration test - multiple)
Ensure importer does not attempt to import a cancelled request (integration test - multiple)
Ensure additional filter/indicator values are “Not specified”/null respectively (integration test - multiple)
Ensure blank and special characters in filter/indicator values are saved accordingly (integration test - multiple)
Ensure archive unpacking stage enqueues the next import stage (unit test - service)
Ensure archive unpacking stage enqueues the next import stage when there is no archive to unpack (unit test - service)
Ensure no status changes occur after import is finished (unit test - service)
Ensure no status changes occur after import is cancelled (unit test - service)
Ensure imported location data can be retrieved successfully (integration test - multiple)
Ensure non-existent location data returns an error (integration test - multiple)
Ensure importing a new location with no code returns an existing old code rather than overwriting (integration test - multiple)
Ensure locations can be imported and treated separately which have: (integration test - multiple)
the same code, but a different name
the same name, but a different code
the same name and code, but a different old code
identical attributes, except for geographic level
identical providers, with a different attribute (e.g. country)
differently cased names
UI Tests
Ensure user upload process completes successfully
uploads CSVs and waits until uploads table appears
table contains expected rows and values
data can be used in data block
Frontend Tests
Ensure “title” field is validated
Ensure form submission will contact the backend with expected data
Ensure data set list contains correct values
Ensure original and file replacement details contain correct values
Ensure replacement plan renders correctly based on import status